## Sheet1
DATE | ACTIVITY | ACCOMPLISHMENT | PROBLEM ENCOUNTER | CONTINUATION OF WORK | SOLUTION FOR THE PROBLEM
Month of December, 2015 | Planning for Concepts of Pet Simulator | Outline/Game flow of Pet Simulator | N/A | Unity Game Engine | N/A
January 1 - 9, 2016 | Studying Unity Game Engine Interface and Essentials | Testing Unity interface | N/A | Unity Scripting | N/A
January 10 - 17, 2016 | Studying Unity C# Scripting | Testing Unity scripting | N/A | Unity Building GUI | N/A
2016-01-18 | Testing touch input | Touch input | Migration of keyboard inputs into touch inputs | Mastering touch inputs | Event Trigger and Keycode
2016-01-19 | Scripting touch inputs | Touch phases concepts | N/A | N/A | N/A
2016-01-20 | Testing UI sizing and scaling | N/A | Sizing the right aspect ratio for the application | Sizing and scaling | N/A
2016-01-21 | Testing UI sizing and scaling | Testing screen orientation | Object references not working in the editor | N/A | using #if (UNITY_EDITOR) #endif and for the proper sizing of aspect ratio of screen orientation solved by using anchors and rect transform
2016-01-22 | Creating main menu of Pet Simulator | Button designing and Dialog | N/A | Scripting button events | N/A
2016-01-23 | Creating main menu of Pet Simulator | Scripting Start and Quit Menu | N/A | N/A | N/A
2016-01-24 | Testing 3d platform view | N/A | Concept of vectors and cameras | Testing 3d platform | N/A